## Timeline
Enterprise Systems Development - Sprint Planning Board (by weeks)
|  |  | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Feb-2021 | Feb-2021 | Feb-2021 | Feb-2021 | Feb-2021 | Feb-2021 | Feb-2021 | Feb-2021 | Feb-2021 | Feb-2021 | Feb-2021 | Feb-2021 | Feb-2021 | Feb-2021 | Feb-2021 | Feb-2021 | Feb-2021 | Feb-2021 | Feb-2021 | Feb-2021 | Feb-2021 | Feb-2021 | Feb-2021 | Feb-2021 | Feb-2021 | Feb-2021 | Feb-2021
| Start | End | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
Assignee - Obiekwe |  |  | 23: Assignee - obiekwe joseph agbu
Assigning of tasks and filling of task delivery form | 23-Nov-2020 | 24-Nov-2020 | 23: Assigning of tasks and filling of task delivery form (23-Nov-20 - 24-Nov-20); 24: Assigning of tasks and filling of task delivery form (23-Nov-20 - 24-Nov-20)
Assignee - Lam,Xue, Obiekwe |  |  | 23: Assignee - Minh,Xue, Obiekwe
Development of initial Gant Chart, Kanban, burn down chart and all relevant visual planning models | 24-Nov-2020 | 25-Nov-2020 | 24: Development of initial Gant Chart, Kanban, burn down chart and all relevant visual planning models (24-Nov-20 - 25-Nov-20); 25: Development of initial Gant Chart, Kanban, burn down chart and all relevant visual planning models (24-Nov-20 - 25-Nov-20)
Assignee - Obiekwe |  |  | 23: Assignee - Obiekwe
Connecting Database to web application | 26-Nov-2020 | 28-Nov-2020 | 26: Connecting Database to web application (26-Nov-20 - 28-Nov-20); 27: Connecting Database to web application (26-Nov-20 - 28-Nov-20); 28: Connecting Database to web application (26-Nov-20 - 28-Nov-20)
Assignee - Lam, Quan |  |  | 23: Assignee - Lam, Quan
Creating all relevant user classes for model | 27-Nov-2020 | 30-Nov-2020 | 27: Creating all relevant user classes for model (27-Nov-20 - 30-Nov-20); 28: Creating all relevant user classes for model (27-Nov-20 - 30-Nov-20); 29: Creating all relevant user classes for model (27-Nov-20 - 30-Nov-20); 30: Creating all relevant user classes for model (27-Nov-20 - 30-Nov-20)
Asignee- Xue, Minh |  |  | 23: Asignee- Xue, Minh
Development of user Login Function | 01-Dec-2020 | 03-Dec-2020 | 1: Development of user Login Function (01-Dec-20 - 03-Dec-20); 2: Development of user Login Function (01-Dec-20 - 03-Dec-20); 3: Development of user Login Function (01-Dec-20 - 03-Dec-20)
Assignee - Minh,Xue, Obiekwe,Lam, Quan |  |  | 23: Assignee - Minh,Xue, Obiekwe,Lam, Quan
Demonstration of Completed tasks and evaluation | 04-Dec-2020 | 04-Dec-2020 | 4: Demonstration of Completed tasks and evaluation (04-Dec-20 - 04-Dec-20)
Assignee - Obiekwe |  |  | 23: Assignee - Obiekwe
Assigning of tasks and filling of task delivery form | 07-Dec-2020 | 07-Dec-2020 | 7: Assigning of tasks and filling of task delivery form (07-Dec-20 - 07-Dec-20)
Assignee - Lam,Xue, Obiekwe |  |  | 23: Assignee - Minh,Xue, Obiekwe,Lam, Quan
Development of updated Gant Chart, Kanban, burn down chart and all relevant visual planning models | 08-Dec-2020 | 08-Dec-2020 | 8: Development of updated Gant Chart, Kanban, burn down chart and all relevant visual planning models (08-Dec-20 - 08-Dec-20)
Assignee - Lam, Quan |  |  | 23: Assignee - Lam, Quan
Development of further model classes | 09-Dec-2020 | 11-Dec-2020 | 9: Development of further model classes (09-Dec-20 - 11-Dec-20); 10: Development of further model classes (09-Dec-20 - 11-Dec-20); 11: Development of further model classes (09-Dec-20 - 11-Dec-20)
Assignee - Obiekwe,Minh,Quan |  |  | 23: Assignee - Obiekwe,Minh, Quan
Initial viewer and swing GUI development | 11-Dec-2020 | 15-Dec-2020 | 11: Initial viewer and swing GUI development (11-Dec-20 - 15-Dec-20); 12: Initial viewer and swing GUI development (11-Dec-20 - 15-Dec-20); 13: Initial viewer and swing GUI development (11-Dec-20 - 15-Dec-20); 14: Initial viewer and swing GUI development (11-Dec-20 - 15-Dec-20); 15: Initial viewer and swing GUI development (11-Dec-20 - 15-Dec-20)
Asignee- Xue, Minh |  |  | 23: Asignee- Xue, Minh
Development of relevant controller classes | 15-Dec-2020 | 17-Dec-2020 | 15: Development of relevant controller classes (15-Dec-20 - 17-Dec-20); 16: Development of relevant controller classes (15-Dec-20 - 17-Dec-20); 17: Development of relevant controller classes (15-Dec-20 - 17-Dec-20)
Assignee - Minh,Xue, Obiekwe,Lam, Quan |  |  | 23: Assignee - Minh,Xue, Obiekwe,Lam, Quan
Demonstration of Completed Tasks and evaluation | 18-Dec-2020 | 18-Dec-2020 | 18: Demonstration of Completed Tasks and evaluation (18-Dec-20 - 18-Dec-20)
Assignee - Obiekwe |  |  | 23: Assignee - Obiekwe
Assigning of tasks and filling of task delivery form | 07-Jan-2021 | 07-Jan-2021 | 7: Assigning of tasks and filling of task delivery form (07-Jan-21 - 07-Jan-21)
Assignee - Lam, Quan |  |  | 23: Assignee - Lam, Quan
Completion of UI | 08-Jan-2021 | 10-Jan-2021 | 8: Completion of UI (08-Jan-21 - 10-Jan-21); 9: Completion of UI (08-Jan-21 - 10-Jan-21); 10: Completion of UI (08-Jan-21 - 10-Jan-21)
Assignee - Obiekwe,Minh |  |  | 23: Assignee - Obiekwe,Minh
Testing of Completed protoype | 11-Jan-2021 | 14-Jan-2021 | 11: Testing of Completed protoype (11-Jan-21 - 14-Jan-21); 12: Testing of Completed protoype (11-Jan-21 - 14-Jan-21); 13: Testing of Completed protoype (11-Jan-21 - 14-Jan-21); 14: Testing of Completed protoype (11-Jan-21 - 14-Jan-21)
Asignee- Xue, Quan |  |  | 23: Asignee- Xue,Quan
Deugging of prototype | 15-Jan-2021 | 18-Jan-2021 | 15: Deugging of prototype (15-Jan-21 - 18-Jan-21); 16: Deugging of prototype (15-Jan-21 - 18-Jan-21); 17: Deugging of prototype (15-Jan-21 - 18-Jan-21); 18: Deugging of prototype (15-Jan-21 - 18-Jan-21)
Assignee - Minh,Xue, Obiekwe,Lam, Quan |  |  | 23: Assignee - Minh,Xue, Obiekwe,Lam, Quan
Evaluation and Blackboard Submission | 19-Jan-2021 | 20-Jan-2021 | 19: Evaluation and Blackboard Submission (19-Jan-21 - 20-Jan-21); 20: Evaluation and Blackboard Submission (19-Jan-21 - 20-Jan-21)
Assignee - Minh,Xue, Obiekwe,Lam, Quan |  |  | 23: Assignee - Minh,Xue, Obiekwe,Lam, Quan
Demonstration of Completed Tasks and Evaluation | 21-Jan-2021 | 21-Jan-2021 | 21: Demonstration of Completed Tasks and Evaluation (21-Jan-21 - 21-Jan-21)